## Sheet1
Date | Task completed | Status | Notes/Challenges & Solutions
2026-02-12 | Added multiple ingredients and mini scale features. | Completed | Used a loop to allow the user to enter ingredients until they type "done"; there were no major issues encountered during this task.
2026-02-13 | Tested code with various inputs. | Completed | Tested small/large numbers, decimals, and scale usage, and it all worked correctly.
2026-02-19 | Saved code in GDB and uploaded to GitHub. | Completed. | Accidentally put Git commands in Python code; deleted them and uploaded via the GitHub website.
2026-02-21 | Created Updated Readme.md. | Completed | Initially, I accidentally put Git commands inside the Python code; I deleted the incorrect commands and uploaded the file via the GitHub website instead.
2026-03-05 | Wrote and revised the Methodology. | Completed | Created and finalized Updated Readme.md;
2026-03-06 | Final check of all 3rd quarter files. | Completed | Verified all 3rd quarter files (docs, code, methodology, etc.)